## WORKS
Procurement Entity |  | ATWIMA KWANWOMA MUNICIPAL ASSEMBLY
Budget Period 2025 | ANNUAL PROCUREMENT PLAN | [6 empty] | Tender Documents
Source of Funding (DACF/DPAT/GOG/IGF/MP-DACF |  |  | BASIC DATA | [5 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
| Duration | [5 empty] | Duration | [5 empty] | Duration
Construrction of 1No. 3 Unit Classroom Block at Bekwaimin | Plan | AR/AKDA/WK/01/25 | 300000 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 300000 | 28/02/2025 | 2025-07-03 | 50000 | 2025-07-06 | 2025-08-12 | 300000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Completion of 1No 3Unit Classroom Block with office, staff common room, 3 seater W/C toilet, provision of overhead tank (Rambo 150) and Mechanisation of existing Borehole at Twedie. | Plan | AR/AKDA/WK/02/25 | 184618.4 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 184618.4 | 28/02/2025 | 2025-07-03 | 150000 | 2025-07-06 | 2025-08-12 | 184618.4
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construrction of 1No. 3 Unit Classroom Block at Trede A | Plan | AR/AKDA/WK/03/25 | 464436 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 464436 | 28/02/2025 | 2025-07-03 | 50000 | 2025-07-06 | 2025-08-12 | 464436
| Actual | [11 empty] | Actual
Construrction of 1No. 3 Unit Classroom Block at Trede B | Plan | AR/AKDA/WK/04/25 | 548650 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 548650 | 28/02/2025 | 2025-07-03 | 50000 | 2025-07-06 | 2025-08-12 | 548650
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construrction of 1No. 3 Unit Classroom Block at Anum Asamoah | Plan | AR/AKDA/WK/04/25 | 36899.8 | NCT | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 36899.8 | 28/02/2025 | 2025-07-03 | 20000 | 2025-07-06 | 2025-08-12 | 36899.8
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construction of Classroom Block by Krofofrom | Plan | AR/AKDA/WK/05/25 | 270000 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 270000 | 28/02/2025 | 2025-07-03 | 400000 | 2025-07-06 | 2025-08-12 | 270000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Drilling and Mechanization of Boreholes at Selected Communities | Plan | AR/AKDA/WK/06/25 | 200000 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 200000 | 28/02/2025 | 2025-07-03 | 4810.26 | 2025-07-06 | 2025-08-12 | 200000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construction of 20- Seater W/C Toilet at Nweneso NO. 3 | Plan | AR/AKDA/WK/07/25 | 173391.45 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 173391.45 | 28/02/2025 | 2025-07-03 | 60883.44 | 2025-07-06 | 2025-08-12 | 173391.45
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construction of Police Station Ampabame NO.2 | Plan | AR/AKDA/WK/08/25 | 600000 | NCT | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 600000 | 28/02/2025 | 2025-07-03 | 49493.14 | 2025-07-06 | 2025-08-12 | 600000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Maintenance of Assembly Offices/ Facility | Plan | AR/AKDA/WK/09/25 | 20000 | RFQ | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 20000 | 28/02/2025 | 2025-07-03 | 300000 | 2025-07-06 | 2025-08-12 | 20000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Maintenance of Markets within the Municipality | Plan | AR/AKDA/WK/10/25 | 5000 | RFQ | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 5000 | 28/02/2025 | 2025-07-03 | 300000 | 2025-07-06 | 2025-08-12 | 5000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construction of Urinals in selected Basic Schools within the municipality | Plan | AR/AKDA/WK/11/25 | 40000 | RFQ | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 40000 | 28/02/2025 | 2025-07-03 | 300000 | 2025-07-06 | 2025-08-12 | 40000
| Actual | [5 empty] | Actual
Maintenance of Feeder Roads within the Municipality | Plan | AR/AKDA/WK/12/25 | 150000 | RFQ | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 150000 | 28/02/2025 | 2025-07-03 | 29599.9 | 2025-07-06 | 2025-08-12 | 150000
Actual
Renovation of Trede Area Council Office | Plan | AR/AKDA/WK/13/25 | 30000 | RFQ | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 30000 | 28/02/2025 | 2025-07-03 | 250000 | 2025-07-06 | 2025-08-12 | 30000
Actual
Construction of Metal Container | Plan | AR/AKDA/WK/14/25 | 30000 | RFQ | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 30000 | 28/02/2025 | 2025-07-03 | 75000 | 2025-07-06 | 2025-08-12 | 30000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Completion of CHIPS Compound at Asaage | Plan | AR/AKDA/WK/15/25 | 170000 | RFQ | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 170000 | 28/02/2025 | 2025-07-03 | 100000 | 2025-07-06 | 2025-08-12 | 170000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construction of Police Station at Awima Boko | Plan | AR/AKDA/WK/16/25 | 300000 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 300000 | 28/02/2025 | 2025-07-03 | 30000 | 2025-07-06 | 2025-08-12 | 300000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Completion of 1 No. 6-Unit Dormitory at Afua Kobi SHS at Traboum | Plan | AR/AKDA/WK/17/25 | 60883.44 | RFQ | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 60883.44 | 28/02/2025 | 2025-07-03 | 50000 | 2025-07-06 | 2025-08-12 | 60883.44
| Actual | [5 empty] | Actual | [5 empty] | Actual
Completion of 1NO. 3-Unit Classroom at Foase | Plan | AR/AKDA/WK/18/25 | 33689.66 | RFQ | No | HoE | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 33689.66 | 28/02/2025 | 2025-07-03 | 15785.24 | 2025-07-06 | 2025-08-12 | 33689.66
| Actual | [5 empty] | Actual | [5 empty] | Actual
Rehabilitation of 50km Feeder Roads within the Municipality | Plan | AR/AKDA/WK/19/25 | 150000 | RFQ | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 150000 | 28/02/2025 | 2025-07-03 | 470000 | 2025-07-06 | 2025-08-12 | 150000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Maintenance of Office and Residencial Building | Plan | AR/AKDA/WK/20/25 | 50000 | RFQ | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 50000 | 28/02/2025 | 2025-07-03 | 450000 | 2025-07-06 | 2025-08-12 | 50000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Construction of Police Station at Atwima Boko | Plan | AR/AKDA/WK/21/25 | 300000 | NCT | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 300000 | 28/02/2025 | 2025-07-03 | 450000 | 2025-07-06 | 2025-08-12 | 300000
| Actual | [5 empty] | Actual | [5 empty] | Actual
Clearing of Refuse Dump Sites | Plan | AR/AKDA/WK/22/25 | 200000 | RFQ | No | ETC | Plan | 2025-05-01 | 25/01/25 | 2025-08-02 | 15/2/2025 | 22/2/2025 | Plan | 300000 | 28/02/2025 | 2025-07-03 | 450000 | 2025-07-06 | 2025-08-12 | 300000
| Actual | [5 empty] | Actual | [5 empty] | Actual

## GOODS
Procurement Entity |  | ATWIMA KWANWOMA MUNICIPAL ASSEMBLY
Budget Period 2025 |  | GOODS |  |  |  |  | Tender Documents
Source of Funding (DACF/DPAT/GOG/IGF | [7 empty] | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  |  | Goods Delivery
Contract Package | Plan vrs Actuals | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission of Tender Eval Report | Approvaval by Final Aothority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature |  | Arrival of goods of Goods
Purchase of Stationeries | Plan | AR/AKDA/GD/01/25 | 63000 | RFQ | ETC | Plan | 2025-01-10 | 17/01/25 | 2025-01-25 | 2025-01-31 | 2025-02-07 | Plan | 63000 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Purchase of Office Equipment | Plan | AR/AKDA/GDS/02/25 | 105000 | NCT | ETC | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | Plan | 105000 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of office Furniture | Plan | AR/AKDA/GD/03/25 | 10000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 10000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Communal Refuse Containers | Plan | AR/AKDA/GD/04/25 | 50000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-07 | Plan | 50000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Sanitary Tools | Plan | AR/AKDA/GD/05/25 | 30000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 30000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Feeding/Refreshmen/ Canteen | Plan | AR/AKDA/GDS/06/25 | 250000 | NCT | ETC | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 250000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Purchase Value Books | Plan | AR/AKDA/GDS/07/25 | 15000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 15000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Medical Supplies/ PPEs | Plan | AR/AKDA/GDS/08/25 | 70000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 70000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Running Cost of Official Vehicle(Fuel & Lub.) | Plan | AR/AKDA/GDS/9/25 | 1200000 | NCT | ETC | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 1200000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Farmers Day Supplies | Plan | AR/AKDA/GDS/10/25 | 60000 | RFQ | ETC | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 60000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Printing of Official Documents/Stationary | Plan | AR/AKDA/GDS/11/25 | 40000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 40000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
People with Disability | Plan | AR/AKDA/GDS/12/25 | 200000 | RFQ | ETC | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 200000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Disaster Relief Supplies | Plan | AR/AKDA/GDS/13/25 | 30000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 30000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Purchase and Maintenance of Streetlights | Plan | AR/AKDA/GDS/14/25 | 50000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 50000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Purchase of Office facilities/supplies | Plan | AR/AKDA/GDS/15/25 | 41500 | NCT | ETC | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 41500 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Purchase of Building and Sport item to Communities with the Municipality | Plan | AR/AKDA/GDS/16/25 | 300000 | NCT | ETC | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 300000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual
Procurement of Dual Desk and Mono Desk to selected Schools | Plan | AR/AKDA/GDS/17/25 | 250000 | NCT | ETC | Plan | 2025-01-11 | 2025-01-31 | 2025-01-25 | 2025-02-01 | 2025-02-08 | Plan | 250000 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08
| Actual |  |  |  |  | Actual | [5 empty] | Actual

## SERVICE
Procurement Entity:ATWIMA KWANWOMA MUNICIPAL ASSEMBLY
Budget Period: JAN-DEC 2025 |  | SERVICES
Source of Funding: IGF/DACF/DDF/GOG | [6 empty] | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract Award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
[6 empty] | Duration |  | 1-2WKS | 1-2WKS | 1WK | 1WK | 1WK | 1WK | Duration | 1WK | 1WK | 1WK |  | 1WK | 1WK | Duration |  | 1-2WK | 1-2WKS
1. Maintenance of Office Equipments | Plan | AR/AKDA/S/DACF/01/25 | 10000 | RFQ | HoE | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 10000 | 2025-03-18 | 2025-03-20 | Plan | 10000 | 2025-03-25 | 2025-04-04 | 15000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
2. Maintenance of Office Generateor/ Grader | Plan | AR/AKDA/S/DACF/02/25 | 15000 | RFQ | ETC | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 15000 | 2025-03-18 | 2025-03-20 | Plan | 15000 | 2025-03-25 | 2025-04-04 | 70000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
3. Train FBOs and market women on alternative livelihood system and package and standardize their commodities | Plan | AR/AKDA/S/IGF/03/25 | 15000 | RFQ | HoE | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 15000 | 2025-03-18 | 2025-03-20 | Plan | 15000 | 2025-03-25 | 2025-04-04 | 20000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
4. Training on Crops and Livestock development/ Agricbusiness development | Plan | AR/AKDA/S/GOG/04/25 | 12000 | RFQ | HoE | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 12000 | 2025-03-18 | 2025-03-20 | Plan | 12000 | 2025-03-25 | 2025-04-04 | 20000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
5. Maintenance of Office Equipment/ Furniture | Plan | AR/AKDA/S/DACF/05/25 | 10000 | RFQ | HoE | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 10000 | 2025-03-18 | 2025-03-20 | Plan | 10000 | 2025-03-25 | 2025-04-04 | 10000
| Actual |  |  | . |  | Actual | [7 empty] | Actual | [6 empty] | Actual
6. Screening of Food Vendors | Plan | AR/AKDA/S/IGF/06/25 | 12000 | RFP | HoE | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 12000 | 2025-03-19 | 2025-03-20 | Plan | 12000 | 2025-03-28 | 2025-04-04 | 5000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
7. Develop and Update of Website/software | Plan | AR/AKDA/S/IGF/07/25 | 20000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 20000 | 2025-03-19 | 2025-03-20 | Plan | 20000 | 2025-03-28 | 2025-04-04 | 30000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
8. Staff/Hon.Members Dev't / Capacity Building | Plan | AR/AKDA/S/GOG/08/25 | 20000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 20000 | 2025-03-19 | 2025-03-20 | Plan | 20000 | 2025-03-28 | 2025-04-04 | 40000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
9. Maintenance of Official Vehicle | Plan | AR/AKDA/S/DACF/09/25 | 83900 | RFP | HoE | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 83900 | 2025-03-19 | 19/03/2022 | Plan | 83900 | 2025-03-28 | 2025-04-04 | 75000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
10. Manpower Skill Development/Office equipment | Plan | AR/AKDA/S/IGF/10/25 | 20000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 20000 | 2025-03-19 | 2025-03-22 | Plan | 20000 | 2025-03-28 | 2025-04-04 | 20000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
11. Maintenance of DRIP Machines | Plan | AR/AKDA/S/IGF/11/25 | 200000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 200000 | 2025-03-19 | 2025-03-22 | Plan | 200000 | 2025-03-25 | 2025-03-28 | 30000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
12. Maintenance of Vehicle and Motorbike | Plan | AR/AKDA/S/GOG/12/25 | 100000 | RFQ | HoE | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 100000 | 2025-03-19 | 2025-03-22 | Plan | 100000 | 2025-03-25 | 2025-03-28 | 50000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
13. Street Naming and Property Address Systerm | Plan | AR/AKDA/CS/DACF/13/25 | 10000 | RFQ | HoE | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 10000 | 2025-03-18 | 2025-03-20 | Plan | 10000 | 2025-03-25 | 2025-04-04 | 80000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
14. Capacity building | Plan | AR/AKDA/S/DACF/14/25 | 20000 | RFQ | HoE | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 20000 | 2025-03-18 | 2025-03-20 | Plan | 20000 | 2025-03-25 | 2025-04-04 | 30000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
15. Formation and training of disaster volunteer groups | Plan | AR/AKDA/S/DACF/15/25 | 5000 | RFQ | HoE | Plan | 2025-01-10 | 2025-01-17 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | Plan | 2025-02-28 | 2025-03-07 | 2025-03-14 | 5000 | 2025-03-18 | 2025-03-20 | Plan | 5000 | 2025-03-25 | 2025-04-04 | 10000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
16. Fumigation | Plan | AR/AKDA/S/DACF/16/25 | 80000 | RFQ | ETC | Plan | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | Plan | 2025-03-01 | 2025-03-08 | 2025-03-15 | 80000 | 2025-03-19 | 2025-03-22 | Plan | 80000 | 2025-03-25 | 2025-03-28 | 161000
| Actual |  |  |  |  | Actual | [7 empty] | Actual